## Slide 1: WP 3
The Qombs Project is funded by the European Union’s Horizon 2020 research and innovation programme under grant agreement number 820419
Martin Franckie
Jerome Faist
Giacomo Scalari
Mattias Beck
Barbara Schneider
Matthew Singleton
Filippos Kapsalidis
Mathieu Bertrand
Josefine Enkner
ETHZ
Mid-term Review meeting
May 13th 2020
Carlo Sirtori
Yanko Todorov
Angela Vasanelli
Azzurra Bigioli
CNRS
Richard Maulini
Antoine Müller
Sargis Hakobyan
ALPES

## Slide 2
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M3
D3.7 M24
Deliverables:

## Slide 3
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M3
D3.7 M24
Deliverables:

## Slide 4: Task 3.1
Goal: Identify and deliver already fabricated, best comb devices @4.5 μm,
from ETH to CNR-INO
Delivered:
dual-waveguide comb QCL at 4.5 μm [1]
two combs at 7.8 μm (for CNRS detector setup)
[1] Y. Bidaux,F. Kapsalidis, P. Jouy, M. Beck, and J. Faist, “Coupled-waveguides for dispersion compensation in semiconductor lasers”, Laser Photonics Rev. 12, 1700323 (2018)

## Slide 5
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M3
D3.7 M24
Deliverables:

## Slide 6: Task 3.2
Goals:
Baseline for QCL comb fabrication
Growth and fabrication of existing designs
Characterize and identify potentials for improvement
Delivered:
Identified several areas for fabrication improvement:
  Dry etching of laser ridges (ETH)
  Radio frequency injection efficiency (ETH)
  Optimizing ridge width (ETH + ALPES)
  Dispersion control via top cladding (ALPES)
ETH sent three 4.5 μm comb devices to CNR-INO

## Slide 7: Task 3.2
Goals:
Baseline for QCL comb fabrication
Growth and fabrication of existing designs
Characterize and identify potentials for improvement
Delivered:
Identified several areas for fabrication improvement:
  Dry etching of laser ridges (ETH)
  Radio frequency injection efficiency (ETH)
  Optimizing ridge width (ETH + ALPES)
  Dispersion control via top cladding (ALPES)
ETH sent three 4.5 μm comb devices to CNR-INO

## Slide 8: Task 3.2
  Dry etching of laser ridges (ETH)
Active
Passive
Heat flux
Status at M1
Ongoing investigations
Problems:
Heat extraction
Lower gain
Dispersion control
~3 μm
Straight walls achieved
Optimizing re-growth
Expect improved:
  Heat extraction
  Gain
  Dispersion control

## Slide 9: Task 3.2
Goals:
Baseline for QCL comb fabrication
Growth and fabrication of existing designs
Characterize and identify potentials for improvement
Delivered:
Identified several areas for fabrication improvement:
  Dry etching of laser ridges (ETH)
  Radio frequency injection efficiency (ETH)
  Optimizing ridge width (ETH + ALPES)
  Dispersion control via top cladding (ALPES)
ETH sent three 4.5 μm comb devices to CNR-INO

## Slide 10: Task 3.2
  Radio frequency injection efficiency (ETH)
Status at M1
Ongoing investigations
Active mode locking:
RF injection close to frep locks comb
Narrow wires:
Poor injection efficiency
Study of RF response due to other factors not possible
RF probe setup
I-V curves
Spectra (Task 3.4)
High RF efficiency:
Figure from:
Hillbrand et al., Nature Photonics 13, 101-104 (2019)
B. Schneider, F. Kapsalidis, M. Singleton, M. Beck and J. Faist
“ RF Study of Quantum Cascade Laser Optical Frequency Combs”
Optical Sensing Autumn School 19, Tromsö
Low-RF-loss QCLs
Low capacitance:
  High-doped subs.
  Top clading
  Narrow waveguide

## Slide 11: Task 3.2
  Radio frequency injection efficiency (ETH)
Status at M1
Ongoing investigations
Active mode locking:
RF injection close to frep locks comb
Narrow wires:
Poor injection efficiency
Study of RF response due to other factors not possible
RF probe setup
I-V curves
Spectra (Task 3.4)
High RF efficiency:
Figure from:
Hillbrand et al., Nature Photonics 13, 101-104 (2019)
B. Schneider, F. Kapsalidis, M. Singleton, M. Beck and J. Faist
“ RF Study of Quantum Cascade Laser Optical Frequency Combs”
Optical Sensing Autumn School 19, Tromsö
~35 dB
Low-RF-loss QCLs
Low capacitance:
  High-doped subs.
  Top clading
  Narrow waveguide

## Slide 12: Task 3.2
Goals:
Baseline for QCL comb fabrication
Growth and fabrication of existing designs
Characterize and identify potentials for improvement
Delivered:
Identified several areas for fabrication improvement:
  Dry etching of laser ridges (ETH)
  Radio frequency injection efficiency (ETH)
  Optimizing ridge width (ETH + ALPES) (results in Task 3.4)
  Dispersion control via top cladding (ALPES)
ETH sent three 4.5 μm comb devices to CNR-INO

## Slide 13: Task 3.2
  Optimizing ridge width (ETH + ALPES)
Narrower ridges, wider spectrum
  6-8 μm: Δν ≈ 60 cm-1
  3-4 μm: Δν ≈ 100 cm-1
ETH
7.8 μm QCL combs
ALPES
6 μm QCL combs
Lower GVD (group velocity dispersion) allow broader combs
GVD tuned by ridge width: Narrower ridge for longer λ
6 μm

## Slide 14: Task 3.2
  Optimizing ridge width (ETH + ALPES)
Narrower ridges, wider spectrum
  6-8 μm: Δν ≈ 60 cm-1
  3-4 μm: Δν ≈ 100 cm-1
ETH
7.8 μm QCL combs
ALPES
6 μm QCL combs
Lower GVD (group velocity dispersion) allow broader combs
GVD tuned by ridge width: Narrower ridge for longer λ
Comb operation

## Slide 15: Task 3.2
Goals:
Baseline for QCL comb fabrication
Growth and fabrication of existing designs
Characterize and identify potentials for improvement
Delivered:
Identified several areas for fabrication improvement:
  Dry etching of laser ridges (ETH)
  Radio frequency injection efficiency (ETH)
  Optimizing ridge width (ETH + ALPES)
  Dispersion control via top cladding (ALPES)
ETH sent three 4.5 μm comb devices to CNR-INO

## Slide 16: Task 3.2
  Dispersion control via top caldding (ALPES)
Highly doped cladding layer added
Wide tuning of GVD
Comparison with/without optimized cladding
Comparing distance from active region
Hakobyan et al., “High performance quantum cascade laser frequency combs at λ ∼ 6 μm based on plasmon-enhanced dispersion compensation” (unpublished)

## Slide 17: Task 3.2
Goals:
Baseline for QCL comb fabrication
Growth and fabrication of existing designs
Characterize and identify potentials for improvement
Delivered:
Identified several areas for fabrication improvement:
  Dry etching of laser ridges (ETH)
  Radio frequency injection efficiency (ETH)
  Optimizing ridge width (ETH + ALPES)
  Dispersion control via top caldding (ALPES)
ETH sent three 4.5 μm comb devices to CNR-INO
D3.3 completed on time (M9)

## Slide 18
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M3
D3.7 M24
Deliverables:

## Slide 19: Task 3.3
ALPES
QCL-combs between 8-10 μm demonstrated by ALPES before Qombs
Using plasmon-enhanced waveguide for GVD compensation
Reproduced results with new growth and processing at 1290 cm-1(λ=7.8 μm)
Very reproducible performance from laser to laser (λ=6 μm)
No limitations from fabrication tolerances: (λ=6 μm)
  Lasing from -10 °C to +50 °C realized for 2.8-5.5 μm waveguides, fab. tol. = ±0.5 μm
Laser 1 beatnote
Laser 2 beatnote
T = -10 °C

## Slide 20: Task 3.3
ALPES
Production of QCL combs is more difficult at λ<8 µm because of higher material GVD
Previously demonstrated dual-waveguide design with passive InGaAs WG requires tight fabrication tolerances
New design with a thin, highly-doped plasmonic layer in the top cladding
No limitations from fabrication tolerances:
  Comb operation from -10 to +50 °C realized for w = 2.8-5.5 μm waveguides,
  Fabrication tolerance ∆w = ±0.5 μm
w = 2.8 µm
w = 5.5 µm
The colored area indicates the currents/temperatures at which comb operation was observed

## Slide 21
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M3
D3.7 M24
Deliverables:

## Slide 22: Task 3.4
Ongoing work (M9-M24)
(expecting delay due to MBE repair and lab lockdown due to COVID-19)
Identified problem areas from Task 3.2
Laser ridge width
RF injection
  Spectrometer incorporated in setup
  Broadens spectrum
Dry etching
  Full active region height etching achieved
Growth and fabrication of designs from WP1
First fabrication of optimized active region done
Broad luminescence, no lasers yet
Giles-Turnois inteferometer (GTI) coatings
Dispersion compensation
Low-loss, high-reflectivity coatings
  Important for quantum optics (WP4)
Optimized 5.5 μm wide waveguide (ETH)

## Slide 23: Task 3.4
Ongoing work (M9-M24)
(expecting delay due to MBE repair and lab lockdown due to COVID-19)
Identified problem areas from Task 3.2
Laser ridge width
RF injection
  Spectrometer incorporated in setup
  Broadens spectrum
Dry etching
  Full active region height etching achieved
Growth and fabrication of designs from WP1
First fabrication of optimized active region done
Broad luminescence, no lasers yet
Giles-Turnois inteferometer (GTI) coatings
Dispersion compensation
Low-loss, high-reflectivity coatings
  Important for quantum optics (WP4)
Optimized 5.5 μm wide waveguide (AL)

## Slide 24: Task 3.4
Ongoing work (M9-M24)
(expecting delay due to MBE repair and lab lockdown due to COVID-19)
Identified problem areas from Task 3.2
Laser ridge width
RF injection
  Spectrometer incorporated in setup
  Broadens spectrum
Dry etching
  Full active region height etching achieved
Growth and fabrication of designs from WP1
First fabrication of optimized active region done
Broad luminescence, no lasers yet
Giles-Turnois inteferometer (GTI) coatings
Dispersion compensation
Low-loss, high-reflectivity coatings
  Important for quantum optics (WP4)
40 cm-1
55 cm-1

## Slide 25: Task 3.4
Ongoing work (M9-M24)
(expecting delay due to MBE repair and lab lockdown due to COVID-19)
Identified problem areas from Task 3.2
Laser ridge width
RF injection
  Spectrometer incorporated in setup
  Broadens spectrum
Dry etching
  Full active region height etching achieved
Growth and fabrication of designs from WP1
First fabrication of optimized active region done
Broad luminescence, no lasers yet
Giles-Turnois inteferometer (GTI) coatings
Dispersion compensation
Low-loss, high-reflectivity coatings
  Important for quantum optics (WP4)
3 μm
9 μm

## Slide 26: Task 3.4
Ongoing work (M9-M24)
(expecting delay due to MBE repair and lab lockdown due to COVID-19)
Identified problem areas from Task 3.2
Laser ridge width
RF injection
  Spectrometer incorporated in setup
  Broadens spectrum
Dry etching
  Full active region height etching achieved
Growth and fabrication of designs from WP1
First fabrication of optimized active region done
Broad luminescence, no lasers yet
Giles-Turnois inteferometer (GTI) coatings
Dispersion compensation
Low-loss, high-reflectivity coatings
  Important for quantum optics (WP4)

## Slide 27: Task 3.4
QCL combs with 70 cm-1 comb spectra and 500 mW output power (AL)
Key achievements
Improved fabrication
λ = 6 μm

## Slide 28: Task 3.4
QCL combs with 70 cm-1 comb spectra and 500 mW output power (AL)
Record low Jth(20°C) = 430 A/cm2 for CW-QCL! (4.5 μm) (AL)
Key achievements
Not a comb yet
Next step:
Cancel GDD with GTI facet coatings
HHL-755
W = 9.3 µm
L = 6 mm
Epi-side down
HR coated

## Slide 29: Task 3.4
QCL combs with 70 cm-1 comb spectra and 500 mW output power (AL)
Record low Jth(20°C) = 430 A/cm2 for CW-QCL! (4.5 μm) (AL)
First observation of increased comb bandwidth due to RF injection (ETH)
40 cm-1
55 cm-1
Key achievements
~35 dB

## Slide 30: Task 3.4
Fabricating improved comb devices at λ=4.5 μm
Growth of optimized active regions at 4.5 μm (from WP1)
Fabricate lasers from optimized λ=8 μm active region (from WP1)
Optimize re-growth for dry-etched waveguides
QCL combs with 70 cm-1 comb spectra and 500 mW output power (AL)
Record low Jth(20°C) = 430 A/cm2 for CW-QCL! (4.5 μm) (AL)
First observation of increased comb bandwidth due to RF injection (ETH)
40 cm-1
55 cm-1
Key achievements
Outlook

## Slide 31
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M3
D3.7 M24
Deliverables:

## Slide 32
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ)
MS3.2 M27 (CNRS)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M10
D3.7 M24
Deliverables:

## Slide 33: Task 3.7
Task 3.7 two parts:
Growth of detector epitaxial layers (ETH)
  Decision (CNRS+ETH) to focus on QCDs
  Designs proposed by CNRS grown (D3.2, M10)
Fabrication of detector devices (CNRS)
  Growths from D3.2 fabricated
  Absorption spectra agree with simulations
  Next generation of detectors required for better temperature performance
On-time delivery of D3.7 challenging due to MBE repairs and COVID-19 lockdown, but realistic

## Slide 34: Task 3.7
Improvements to QCD fabrication (CNRS)
Goals:
High bandwidth (> 20 GHz)
Flat transmission
Challenge:
Impedance mis-match
Impedance matching typically narrow band
Current solution:
Klopfenstein profiling*:
*R. Klopfenstein, “A transmission line taper of improved design”, Proc. IRE 44, pp. 31-35 (1956)

## Slide 35: Summary
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ) “Improved QCL combs” (finalized with D3.4)
MS3.2 M27 (CNRS) “Improved QCDs or QWIPs” (finalized with D3.7)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M10
D3.7 M24
Deliverables:

## Slide 36: Summary
Tasks:
T3.1 M1-M3: Identification of existing QCL-comb devices (ETHZ)
T3.2 M3-M9: QCL-comb fabrication using existing technology and AR designs (ETHZ)
T3.3 M3-M9: Fabrication tolerances (ALPES)
T3.4 M9-M24: Fabrication and basic characterization of new comb devices (ETHZ)
T3.5 M25-M33: Further generation of devices (ETHZ)
T3.6 M24-M36: Mass production of improved devices (ALPES)
T3.7 M1-M24 : Fabrication of QCDs (CNRS + ETHZ)
Milestones
MS3.1 M24 (ETHZ) “Improved QCL combs” (finalized with D3.4)
MS3.2 M27 (CNRS) “Improved QCDs or QWIPs” (finalized with D3.7)
D3.1 M3
D3.3 M9
D3.4 M24
D3.5 M33
D3.6 M30
D3.2 M10
D3.7 M24
Deliverables:
Thank you for your attention

## Slide 37: Task 3.7
Improvements to QCD fabrication (CNRS)
Goals:
High bandwidth (> 20 GHz)
Flat transmission
Challenge:
Impedance mis-match
Impedance matching typically narrow band
Possible solutions:
Klopfenstein profiling*:
Air bridge:
Resonant co-planar waveguides:
*R. Klopfenstein, “A transmission line taper of improved design”, Proc. IRE 44, pp. 31-35 (1956)

## Slide 38: MBE breakdown
Nov 2, 2018: Growth of record temperature THz QCL
Nov 26, 2018: Al cell failed
Dec 2018: MBE opened for repair D3.2 planned
Feb 2019: MBE operational again
  MBE in good condition
  Low background doping
Mar 2019: wafer rotation failed
  MBE opened under Argon purge
  Wafer manipulator extracted inside glove bag
  2/3 bearings broken
April 2019: New bearings delivered
May 2019: System under vacuum
June 2019: Calibrations, MBE operational
July 2019: wafer rotation failed
  Growth of layers for D3.2 (delayed to M10)
Aug 2019: further short growth sessions with unstable rotation
M2
M3
M5
M6
M7
M8
M9
M10
M11

## Slide 39: MBE breakdown
Sept 2019: Preparing for opening
  Argon purge to minimize moisture
  Glove box
  Removed entire manipulator
  Ordering of rare parts
Oct 2019: Opening, repairs done
Nov 2019: Closing, baking, recovering vacuum
Jan-Feb 2020: Calibrations, heating cells
Mar 2020: COVID-19 lockdown of ETH
M12
M13
M14
M16
M18
Nov 2, 2018: Growth of record temperature THz QCL
Nov 26, 2018: Al cell failed
Dec 2018: MBE opened for repair D3.2 planned
Feb 2019: MBE operational again
  MBE in good condition
  Low background doping
Mar 2019: wafer rotation failed
  MBE opened under Argon purge
  Wafer manipulator extracted inside glove bag
  2/3 bearings broken
April 2019: New bearings delivered
May 2019: System under vacuum
June 2019: Calibrations, MBE operational
July 2019: wafer rotation failed
  Growth of layers for D3.2 (delayed to M10)
Aug 2019: further short growth sessions with unstable rotation
M2
M3
M5
M6
M7
M8
M9
M10
M11

## Slide 40: MBE breakdown
Sept 2019: Preparing for opening
  Argon purge to minimize moisture
  Glove box
  Removed entire manipulator
  Ordering of rare parts
Oct 2019: Opening, repairs done
Nov 2019: Closing, baking, recovering vacuum
Jan-Feb 2020: Calibrations, heating cells
Mar 2020: COVID-19 lockdown of ETH
M12
M13
M14
M16
M18
Nov 2, 2018: Growth of record temperature THz QCL
Nov 26, 2018: Al cell failed
Dec 2018: MBE opened for repair D3.2 planned
Feb 2019: MBE operational again
  MBE in good condition
  Low background doping
Mar 2019: wafer rotation failed
  MBE opened under Argon purge
  Wafer manipulator extracted inside glove bag
  2/3 bearings broken
April 2019: New bearings delivered
May 2019: System under vacuum
June 2019: Calibrations, MBE operational
July 2019: wafer rotation failed
  Growth of layers for D3.2 (delayed to M10)
Aug 2019: further short growth sessions with unstable rotation
M2
M3
M5
M6
M7
M8
M9
M10
M11
Current status (M20)
May 5, 2020: First growth
May 11-22: Growth of GaAs to purify system,
callibrate doping
May 25-Jun 5: Melt Al cell, de-gas and grow
AlAs to purify further
Jun 8: Resuming growth of QCLs and QCDs
(M21)

## Slide 41: Implications for the Project
Task | Deliverable | Risk | Reason and mitigation
T3.4 (M9-24) | D3.4 (M24) | Low | MBE expected online June 2020. Little time for growth of new QCLs. Worst case: growth by Alpes.
T3.5 (M24-33) | D3.5 (M33) | Very low | Still plenty of time for growth of final QCL devices.
T3.7 (M1-24) | D3.7 (M24) | Very low | If grown detectors do not work, second growth is necessary. D3.7 delayed iff QCDs and MBE fails.
T1.5 (M1-24) | D1.3 (M24) | No risk | Input from D3.4 useful for further optimization. If no input is received or delayed, T1.2-T1.4 is enough.
T4.1.2 (M6-M36) | D4.3 (M24) | Very low | Iff D3.4 is significantly delayed will this be affected.
T4.4.2 (M7-24) | D4.3 (M24) | Very low | Same as above
T4.3 (M12-36) | D4.4 (M30) | Very low | Iff D3.7 is significantly delayed will this be affected.

## Slide 42: Dissemination
Publications
Conference contributions
Hakobyan et al., “High performance quantum cascade laser frequency combs at λ ∼ 6 μm based on plasmon-enhanced dispersion compensation” Optics Express (2020)
Biglioni et al., “Mixing properties of room temperature patch-antenna receivers in a mid-infrared (λ~9 μm) heterodyne system” Laser & Photonics Reviews 14, 1900207 (2020)
S. Hakobyan et al., CLEO 2020, Online, 11.-15.5.2020
S. Hakobyan et al., SPIE DCS, Online, 27.4.-8.5.2020
M. Franckie et al., CLEO Europe, Munich, 23.-26.7.2019
M. Franckie et al., EDISON 21, Nara, Japan, 14.-19-7-2019
M. Franckie et al., SPS Annual Meeting, Zurich, 26.-30.8-2019
M. Franckie et al., ITMMW-THz, Paris. 1.-6.9.2019
M. Franckie et al., ITQW, Ojai, CA, USA, 15.-20.9.2019
J. Enkner et al., Summer School, Vienna, 16.-20-9-2019
B. Schneider et al., Optical Sensing Autumn School 19, Tromsö,Finland, 27.10.-1.11.2019

## Slide 43: Conference contributions
EDISON 21, Nara: New Frontiers for THz Quantum Cascade Lasers:
NEGF Optimization and Fabrication of Devices Operating Above 205 K
M. Franckie, L. Bosco, M. Beck, and J. Faist
ITQW, Ojai Valley, USA 2019: Two-Quantum Well THz Quantum Cascade Lasers Operating Up To 210 K
M. Franckié, L. Bosco, M. Beck, E. Mavrona, A. Wacker, J. Faist
CLEO Europe, Munich 2019: Optimization and fabrication of two-quantum well THz QCLs operating above 200 K
M. Franckie, L. Bosco, M. Beck, E. Mavrona, A. Wacker, G. Scalari, J. Faist
SPS annual meeting, Zürich 2019: Thermoelectrically cooled THz Quantum Cascade Lasers operating up to 210 K.
L. Bosco, M. Franckie, M. Beck, G. Scalar, A. Wacker, J. Faist
IRMMW-THz, Paris 2019: THz Quantum Cascade Lasers Operating up to 210 K
M. Franckié, L. Bosco, E. Mavrona, A. Wacker, and J. Faist
Optical Sensing Autumn School 19, Tromsö: RF Study of Quantum Cascade Laser Optical Frequency Combs B. Schneider, F. Kapsalidis, M. Singleton, M. Beck and J. Faist
SPIE DCS, Online 2020: High performance QCL frequency comb at 6 µm.
Sargis Hakobyan, Richard Maulini, Stéphane Blaser, Tobias Gresch, and Antoine Muller
CLEO 2020, Online 2020: High performance quantum cascade laser frequency combs at ~6 μm S. Hakobyan, R. Maulini, S. Blaser, T. Gresch, Y. Francescato, A. Muller, P. Allmendinger, M. Mangold, P. Jouy, and A. Hugi

## Slide 44: Simulation of QCL squeezing
Three-mode QCL, strong pump treated classically (coherent state)
Effective Hamiltonian of the system:
Solving Heisenberg – Langevin equations of motion for quadrature d(φ)
Params: no loss, no gain
Params: loss=0.2 J, no gain
χ(3)
Lasing mode
Gain
a
b
Preliminary results

## Slide 45: Simulation of QCL squeezing
Three-mode QCL, strong pump treated classically (coherent state)
Effective Hamiltonian of the system:
Solving Heisenberg – Langevin equations of motion for quadrature d(φ)
Params: no loss, no gain
Params: loss=0.2 J, g(t=0) =0.7J
χ(3)
Lasing mode
Gain
a
b
Preliminary results

## Slide 46: Simulation of QCL squeezing
Three-mode QCL, strong pump treated classically (coherent state)
Effective Hamiltonian of the system:
Solving Heisenberg – Langevin equations of motion for quadrature d(φ)
Params: no loss, no gain
Params: loss=0.2 J, g(t=0) =0.7J
χ(3)
Lasing mode
Gain
a
b
Preliminary results
Under circumstances with large J compared to gain,
squeezing achievable